## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-04-02 |  |  |  |  | April | [27 empty] | May
Scrolling Increment: | 1 | time axis 2022-04-03 to 2022-05-28
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-04-03 to 2022-05-28
TITLE 1
Task 1 | Goal | Name | 25% | 2022-04-02 | 3 | 2022-04-03: 2; 2022-04-04: 2
Task 2 | Milestone |  |  | 2022-04-07 | 1 | bar: 2022-04-07
Task 3 | Low Risk |  | 50% | 2022-03-30 | 10
Task 4 | Milestone |  |  | 2022-04-22 | 1 | bar: 2022-04-22
Task 5 | Med Risk |  | 10% | 2022-04-08 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-04-08 | 13
Task 2 | On Track |  | 50% | 2022-04-10 | 9
Task 3 | Low Risk |  | 33% | 2022-04-15 | 11
Task 4 | Milestone |  |  | 2022-04-17 | 1 | bar: 2022-04-17
Task 5 |  |  |  | 2022-04-18 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-04-17 | 4
Task 2 | Med Risk |  |  | 2022-04-20 | 14
Task 3 | On Track |  |  | 2022-05-05 | 6
Task 4 | Goal |  |  | 2022-05-09 | 3 | 2022-05-09: 2; 2022-05-10: 2; 2022-05-11: 2
Task 5 | Low Risk |  |  | 2022-04-08 | 19
TITLE 4
Task 1 |  |  |  | 2022-05-12 | 15
Task 2 |  |  |  | 2022-05-26 | 5
Task 3 | Milestone |  |  | 2022-07-07 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
Systems Coursework
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-02-04 |  |  |  |  | February | [20 empty] | March
Scrolling Increment: | 4 | time axis 2022-02-08 to 2022-04-07
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
TITLE 1
Create Gantt chart | High Risk | Tom | 100% | 2022-02-04 | 2
User login/logoff | High Risk | Tom | 100% | 2022-02-04 | 4
Ls Command | High Risk | Kypros | 100% | 2022-02-06 | 3
Cp Command | High Risk | Tom | 100% | 2022-02-07 | 6
mv command | High Risk | Tom | 100% | 2022-02-13 | 3
TITLE 2
mkdir Command | High Risk | Kypros | 100% | 2022-02-08 | 6
rmdir Command | High Risk | Kypros | 100% | 2022-02-13 | 3
pwd command | High Risk | Kypros | 100% | 2022-02-15 | 6
ps Command | High Risk | Tom | 100% | 2022-02-15 | 6
Which command | High Risk | Tom | 100% | 2022-02-20 | 3
TITLE 3
http server | High Risk | Kypros | 100% | 2022-02-20 | 10
javaFX | High Risk | Tom | 100% | 2022-02-22 | 6
Exchanging messages | High Risk | Tom | 100% | 2022-02-27 | 5
whoami command | Low Risk | Tom | 100% | 2022-03-03 | 4
super command | Low Risk | Kypros | 100% | 2022-03-02 | 12
TITLE 4
adduser command | Low Risk | Tom | 100% | 2022-03-06 | 5
Deluser command | Low Risk | Tom | 100% | 2022-03-10 | 5
chpass command | Low Risk | Tom | 100% | 2022-03-14 | 7
use case diagram | Med Risk | Kypros | 100% | 2022-03-18 | 8
Activity diagram | Med Risk | Tom | 100% | 2022-03-20 | 4
sequence diagram | Med Risk | Tom | 100% | 2022-03-23 | 5
State Diagram | Med Risk | Kypros | 100% | 2022-03-25 | 9
Class Diagram | Med Risk | Kypros | 100% | 2022-04-01 | 2
Risk Analysis | High Risk | Kypros | 100% | 2022-04-02 | 2
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-04-02 |  |  |  |  | April | [27 empty] | May
Scrolling Increment: | 5 | time axis 2022-04-07 to 2022-06-01
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-04-07 to 2022-06-01
TITLE 1
Task 1 | Goal | Name | 25% | 2022-04-02 | 3
Task 2 | Milestone |  |  | 2022-04-07 | 1 | bar: 2022-04-07
Task 3 | Low Risk |  | 50% | 2022-03-30 | 10
Task 4 | Milestone |  |  | 2022-04-22 | 1 | bar: 2022-04-22
Task 5 | Med Risk |  | 10% | 2022-04-08 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-04-08 | 13
Task 2 | On Track |  | 50% | 2022-04-10 | 9
Task 3 | Low Risk |  | 33% | 2022-04-15 | 11
Task 4 | Milestone |  |  | 2022-04-17 | 1 | bar: 2022-04-17
Task 5 |  |  |  | 2022-04-18 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-04-17 | 4
Task 2 | Med Risk |  |  | 2022-04-20 | 14
Task 3 | On Track |  |  | 2022-05-05 | 6
Task 4 | Goal |  |  | 2022-05-09 | 3 | 2022-05-09: 2; 2022-05-10: 2; 2022-05-11: 2
Task 5 | Low Risk |  |  | 2022-04-08 | 19
TITLE 4
Task 1 |  |  |  | 2022-05-12 | 15
Task 2 |  |  |  | 2022-05-26 | 5
Task 3 | Milestone |  |  | 2022-07-07 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one